DETAILED SPRINT PLAN — 14 SPRINTS / 28 WEEKS

Sprint Delivery Plan

DX Student Help — Web & Mobile Learning Support Platform

| Document control | Details |
| --- | --- |
| Client | The X Student Help (PTY) LTD, Durban, South Africa |
| Client representative | Thabo Mkhize |
| Prepared by | Mayura Consultancy Services (MCSpoorthi IT Solutions Private Limited) |
| Version / status | 1.0 — for client review |
| Date | 6 October 2026 |
| Related documents | DX Student Help BRD and SRS; Quotation MCS-DX-2026-001 |

# 1. Purpose of this Document

This document sets out exactly how DX Student Help will be built: the delivery approach, what happens in each of the fourteen two-week sprints, what DX receives at the end of each one, what DX must provide, and how each sprint is accepted. It replaces the twelve-sprint outline in the earlier project plan.

The plan now includes the platform improvements agreed after the first review: curriculum-aware subject launch controls, tutor recognition, academic honesty and copyright safeguards, age-mismatch review, mobile number capture for future SMS and WhatsApp messaging, low-data mode, offline downloads, product analytics, in-app support, designed empty states, an institution register, multilingual groundwork, a fully admin-controlled monetisation engine and live payments.

# 2. Delivery Approach

## 2.1 Sprint rhythm

Work runs in two-week sprints. Every sprint follows the same pattern, so DX always knows what is happening and never waits more than two weeks to see progress.

| Stage | What happens |
| --- | --- |
| Sprint planning (day 1) | The team confirms the sprint backlog and acceptance criteria with DX. Anything unclear is resolved before work starts. |
| Build (days 1–9) | Development, with quality assurance running alongside from Sprint 4 rather than at the end. |
| Internal review (day 9) | The team tests the sprint output on staging and fixes defects before showing it. |
| Sprint review (day 10) | Live demonstration of working software on staging. DX gives feedback and accepts the sprint. |
| Acceptance & invoice | DX confirms acceptance within 3 business days. The sprint is then invoiced. |

## 2.2 Definition of done

- Acceptance criteria met and demonstrated on staging.

- Code reviewed, automated tests passing, static analysis clean in the CI pipeline.

- Security and permission checks applied to every new endpoint and screen.

- Responsive from 360 px upwards and accessible to WCAG 2.1 AA.

- Documentation and the API specification updated.

## 2.3 Technology

| Layer | Technology |
| --- | --- |
| Backend & API | Laravel 11, PHP 8.3, REST API (versioned), queues and scheduler |
| Front end | React 19 with TypeScript, Inertia.js, Tailwind CSS, shadcn/ui, Vite |
| Mobile | Progressive Web App plus Android and iOS apps packaged with Capacitor from the same React code base |
| Data | MySQL 8 or MariaDB 10.6+ (confirmed in Sprint 1), Redis for cache, sessions and queues, off-server object storage |
| Infrastructure | Client VPS managed through WHM, Nginx, Supervisor, Cloudflare, automated encrypted off-server backups |
| Delivery | GitHub single repository, GitHub Actions for test, build and deploy, Codemagic for signed mobile builds |
| Quality | Pest tests, PHPStan static analysis, OWASP security testing, load testing |

## 2.4 Team

| Role | Engagement |
| --- | --- |
| Project Manager / Business Analyst | Throughout: planning, requirements, sprint reviews, reporting |
| UI/UX Designer | Sprints 1–3 in full, then on call for refinements |
| 2 × Full-stack Developers (Laravel + React) | Sprints 3–14 |
| QA Engineer | Sprints 4–14 |
| DevOps Engineer | Sprint 3 and Sprints 13–14, part-time in between |

## 2.5 Communication and change control

- Weekly status call covering progress, risks and decisions needed.

- Sprint review every two weeks with a live demonstration.

- Shared backlog visible to DX at all times.

- Any change to agreed scope is estimated in hours and cost, and approved in writing before work starts. Small refinements inside an agreed feature are absorbed.

- DX responses and decisions within 3 business days; delays move the timeline by the same amount.

# 3. Sprint Roadmap

| Sprint | Weeks | Focus | Payment (ZAR) |
| --- | --- | --- | --- |
| 1 | 1–2 | Discovery & Requirements | 65,000 |
| 2 | 3–4 | Design System & Core Student Experience | 65,000 |
| 3 | 5–6 | Remaining Designs, Prototype & Environments | 65,000 |
| 4 | 7–8 | Identity, Roles, Security & Curriculum Engine | 65,000 |
| 5 | 9–10 | Onboarding, Guardian Consent & Personalisation | 65,000 |
| 6 | 11–12 | Tutor Onboarding, Verification & Coverage | 65,000 |
| 7 | 13–14 | Help Requests & Matching Engine | 65,000 |
| 8 | 15–16 | Messaging, Safeguarding & Ratings | 65,000 |
| 9 | 17–18 | Learning Resources, Offline Access & Announcements | 65,000 |
| 10 | 19–20 | Community & Moderation | 65,000 |
| 11 | 21–22 | Progress, Tutor Recognition, Analytics & Low-Data Mode | 65,000 |
| 12 | 23–24 | Admin Console, Reports, Monetisation Engine & In-App Support | 65,000 |
| 13 | 25–26 | Payments & Subscriptions, PWA & Store Apps | 65,000 |
| 14 | 27–28 | Hardening, UAT, Store Submission & Go-Live | 65,000 |
| — | +60 days | Hypercare, warranty and handover | Included |

The first demonstrable software appears in Sprint 3 and every sprint from then on ends with working software on a live staging environment that DX can use.

# 4. Sprint Detail

Each sprint below lists its objective, the work performed, what DX receives, what DX must provide, and how the sprint is accepted.

## Sprint 1 — Discovery & Requirements

| Item | Detail |
| --- | --- |
| Weeks | Weeks 1–2 |
| Effort | 157 hours |
| Payment on acceptance | ZAR 65,000 |
| Sprint demo | Walkthrough of the requirements specification, journey maps and backlog |

Objective: Turn the DX Student Help concept into a signed-off, buildable specification, and settle the policy, safety and commercial decisions that shape the product.

### Business analysis

- Kick-off workshop: vision, launch audience, success measures, priorities.

- User journey maps for Students (minor and adult), Tutors, Moderators and Administrators.

- Help-request lifecycle and tutor matching rules, including escalation and reassignment.

- Tutor onboarding, vetting and recognition model.

- Subject launch strategy: which subjects go live first and the minimum tutor coverage per subject.

- Monetisation model: free-for-everyone versus freemium, free allowance, grandfathering and override rules.

### Curriculum & data

- Curriculum model: pathways, institution types, Grades 8–12, NCV and NATED programmes, qualifications, years, faculties, subjects.

- Institution model (schools, colleges, universities) for future school-level reporting.

- Collect master curriculum data from DX.

### Compliance & safety

- POPIA approach: guardian consent for under-18s, consent records, data subject rights, retention periods.

- Safeguarding controls: on-platform messaging, contact masking, moderation visibility, reporting and blocking.

- Academic honesty policy and copyright/upload declaration policy.

- Age-mismatch review rules (adult date of birth combined with a school grade).

### Technical planning

- Confirm architecture and stack: Laravel 11 API with Inertia and React 19 (TypeScript), MySQL/MariaDB decision, Redis, Capacitor for store apps.

- VPS and WHM review, environment plan, domain and DNS plan, backup and monitoring approach.

- Account and dependency checklist with owners and deadlines (Section 7).

- Prioritised backlog with acceptance criteria for every requirement.

### Deliverables

- Software Requirements Specification (final, superseding v0.9)

- Updated BRD with monetisation and safety decisions

- User journey maps and curriculum/institution data model

- Prioritised backlog with acceptance criteria

- Account and dependency checklist with dates

### Needed from DX during this sprint

- Decision-makers available for two workshops

- Curriculum master data and brand assets

- Decisions on consent method, minimum age, tutor vetting documents and monetisation model

- Start of Apple and Google account registration (D-U-N-S can take 1–3 weeks)

Acceptance: DX signs off the SRS and backlog.

## Sprint 2 — Design System & Core Student Experience

| Item | Detail |
| --- | --- |
| Weeks | Weeks 3–4 |
| Effort | 157 hours |
| Payment on acceptance | ZAR 65,000 |
| Sprint demo | Design system and clickable onboarding prototype |

Objective: Establish the DX visual identity as a reusable React component library and design the screens students use most.

### Design system

- Colour palette, typography, icon set, spacing scale and component library (buttons, forms, cards, navigation, modals, toasts).

- Accessibility baseline: WCAG 2.1 AA contrast, focus states, labels, touch targets.

- Dark mode tokens and mobile-first layout rules from 360 px upwards.

### Student screens

- Registration, guardian consent, email verification.

- Pathway selection and the School, College and University sub-flows.

- Grade and subject selection with live selection tracker.

- Student dashboard, help request creation, request detail with chat, profile and settings.

- First-run empty states for every list screen, each with a clear next action.

### Front-end foundation

- React 19 + TypeScript component library scaffolded with Tailwind and shadcn/ui, matching the design tokens.

- Storybook-style component catalogue for consistent reuse.

### Deliverables

- Design system and React component library

- Student-facing high-fidelity screens

- Clickable onboarding prototype

### Needed from DX during this sprint

- Consolidated design feedback within 3 business days

Acceptance: DX approves the design system and student screens.

## Sprint 3 — Remaining Designs, Prototype & Environments

| Item | Detail |
| --- | --- |
| Weeks | Weeks 5–6 |
| Effort | 157 hours |
| Payment on acceptance | ZAR 65,000 |
| Sprint demo | Full clickable prototype plus live staging environment with automated deployment |

Objective: Complete all designs and stand up the technical foundation so that every later sprint ends on a live, testable environment.

### Design completion

- Tutor workspace: profile, verification upload, request queue, conversations, recognition and resources.

- Resource library, offline downloads, announcements, community, progress screens.

- Admin console: users, tutors, curriculum, moderation, announcements, reports, monetisation settings.

- Full clickable prototype; usability walkthrough with students and tutors arranged by DX; up to two revision rounds.

### Environments & delivery pipeline

- VPS preparation via WHM: PHP 8.3 extensions, Composer, database, Redis, Supervisor, cron, SSH deploy user, SSL.

- Staging and production cPanel accounts with separate databases and isolated storage.

- GitHub repository, branching model and GitHub Actions: tests, static analysis, Vite build, deploy over SSH.

- Automated encrypted backups to off-server storage, uptime monitoring and error tracking.

- Transactional email service configured with SPF, DKIM and DMARC on the DX domain.

### Deliverables

- Complete high-fidelity designs (approximately 60–70 screens) and clickable prototype

- Staging environment live with one-click deployment

- Backup, monitoring and email delivery operational

### Needed from DX during this sprint

- 5–8 students and tutors for the usability walkthrough

- VPS root access, domain DNS control, email service account

Acceptance: DX approves the final prototype; a code change is demonstrated deploying automatically to staging.

## Sprint 4 — Identity, Roles, Security & Curriculum Engine

| Item | Detail |
| --- | --- |
| Weeks | Weeks 7–8 |
| Effort | 157 hours |
| Payment on acceptance | ZAR 65,000 |
| Sprint demo | Sign-up, login, admin invitations and curriculum administration on staging |

Objective: Build the secure core that every later feature depends on, and the curriculum engine that drives all personalisation.

### Identity & access

- Registration for Student and Tutor only, with validation, password policy and breached-password checks.

- Email verification, password reset, account lockout after repeated failures, session management.

- Mobile number capture with OTP verification, so SMS and WhatsApp channels can be enabled later without chasing users.

- Role-based access control for Student, Tutor, Moderator, Administrator and Super Administrator.

- Administrator accounts by invitation only, with mandatory multi-factor authentication.

- Terms and privacy policy acceptance records; personal data export and deletion request handling.

### Curriculum & institutions

- Curriculum engine: pathways, institution types, tracks, qualifications, grades, levels, years, faculties and subjects, all admin-managed.

- Bulk import from a CSV template with row-level validation.

- Institution register (schools, colleges, universities) with provinces, ready for school-level reporting later.

### Platform services

- Notification service with pluggable channel drivers (in-app, email now; SMS and WhatsApp ready).

- Audit logging, rate limiting, secure headers, encrypted secrets, private file storage.

- Multilingual groundwork: all interface text in translation files, locale stored per user.

- QA engineer joins: test plan, automated test framework, CI gates.

### Deliverables

- Working authentication, roles and admin invitations on staging

- Curriculum and institution administration loaded with DX data

- Audit log and notification service in place

### Needed from DX during this sprint

- Curriculum master data (if not supplied in Sprint 1)

- Draft terms of use and privacy policy from DX's attorney

Acceptance: Scripted tests pass for registration, login, MFA, role restrictions and curriculum management.

## Sprint 5 — Onboarding, Guardian Consent & Personalisation

| Item | Detail |
| --- | --- |
| Weeks | Weeks 9–10 |
| Effort | 157 hours |
| Payment on acceptance | ZAR 65,000 |
| Sprint demo | End-to-end journey from registration to a personalised dashboard, for a minor and an adult |

Objective: Deliver the complete, POPIA-compliant onboarding journey and the personalised dashboard that follows from it.

### Onboarding

- Pathway selection and all three sub-flows driven entirely by curriculum configuration.

- Grade, programme, qualification, year, faculty and subject selection with live tracker.

- Optional institution selection with free-text fallback.

- Profile management, including changing academic context later with immediate re-personalisation.

### Guardian consent

- Guardian details captured for under-18 registrations.

- Consent request by email (and SMS-ready) with approve and decline, valid 7 days and re-sendable.

- Restricted mode until consent: browse resources and announcements, no requests, messaging or posting.

- Consent records with timestamp, IP address and policy version; consent withdrawal; automatic lifting at 18.

- Age-mismatch flagging into an admin review queue; account treated as a minor until reviewed.

### Personalisation

- Personalised dashboard: open requests, suggested resources, targeted announcements, community activity, progress summary.

- Subject visibility rules so only subjects with sufficient tutor coverage are offered, with notify-me on the rest.

- Designed empty states throughout for new accounts.

### Deliverables

- Full onboarding for all three pathways on staging

- Guardian consent flow with consent records visible in the admin console

- Personalised dashboard with empty states

Acceptance: DX completes scripted onboarding tests as a School, College and University user, and as a minor requiring consent.

## Sprint 6 — Tutor Onboarding, Verification & Coverage

| Item | Detail |
| --- | --- |
| Weeks | Weeks 11–12 |
| Effort | 157 hours |
| Payment on acceptance | ZAR 65,000 |
| Sprint demo | Tutor registration through to admin approval, plus the subject coverage dashboard |

Objective: Bring tutors onto the platform and give DX the tools to build and monitor tutor supply before launch.

### Tutor experience

- Tutor profile: photo, bio, qualification, institution, subjects and levels supported, languages, weekly availability.

- Verification document upload (ID, qualifications, police clearance as configured) to private storage.

- Availability toggle that removes a tutor from matching temporarily.

- Tutor agreement acceptance, including the academic honesty undertaking.

### Verification workflow

- Admin review queue with secure, time-limited document access.

- Approve or reject with mandatory reason; tutor notified; resubmission supported.

- Suspend or deactivate a tutor, returning any open requests to matching.

### Supply management

- Subject coverage dashboard showing verified tutors per subject and level, and which subjects fall below the launch threshold.

- Subject go-live rules driven by minimum coverage, so students never see a subject with no tutors.

- Tutor invitation links and a pre-registration flow DX can share during recruitment.

### Deliverables

- Tutor onboarding and verification working on staging

- Subject coverage dashboard

- Tutor recruitment can begin immediately

### Needed from DX during this sprint

- Final list of required verification documents

- Start of tutor recruitment using the live staging flow

Acceptance: DX approves and rejects a real tutor end to end and reviews the coverage dashboard.

## Sprint 7 — Help Requests & Matching Engine

| Item | Detail |
| --- | --- |
| Weeks | Weeks 13–14 |
| Effort | 157 hours |
| Payment on acceptance | ZAR 65,000 |
| Sprint demo | A student request routed to tutors, accepted, reassigned and escalated |

Objective: Deliver the core of the platform: students raising structured requests and being matched to the right tutors.

### Raising a request

- Structured request: subject from the student's selections, topic, description and up to five attachments.

- Client-side image compression for phone photos to reduce data use.

- Academic honesty confirmation on the request form.

- Request quota check built in from day one (unlimited while the platform is free).

- Expected response time shown from real platform data.

### Matching

- Eligibility rules: verified, active, available, supporting the subject, level and pathway.

- Notification to eligible tutors, request queue, first-to-accept assignment, decline with reason.

- Escalation after the configured time, with admin notification and manual assignment.

- Reassignment, cancellation, resolution, student confirmation and auto-close after 72 hours.

- Unmatched questions offered to the community as a fallback.

### Request management

- Student request history with status and last activity; tutor views for available, active and completed requests.

- Request statuses, timestamps and full history retained for reporting.

### Deliverables

- Complete help request and matching flow on staging

- Escalation and admin assignment tools

Acceptance: DX completes a scripted test covering accept, decline, escalate, reassign, resolve and auto-close.

## Sprint 8 — Messaging, Safeguarding & Ratings

| Item | Detail |
| --- | --- |
| Weeks | Weeks 15–16 |
| Effort | 157 hours |
| Payment on acceptance | ZAR 65,000 |
| Sprint demo | A live student–tutor conversation, a safeguarding report and a moderator action |

Objective: Make conversations work in real time and make them safe, which is the single most important requirement for a platform used by minors.

### Messaging

- Real-time in-request conversation with text, images and PDF attachments.

- Delivery, read and typing indicators; offline queueing of unsent messages.

- Conversations become read-only once a request closes.

### Safeguarding

- Automatic masking of phone numbers, email addresses, social handles and external links, with an explanation shown to the sender.

- Prohibited-word list with automatic flagging for moderator review.

- Report and block from within a conversation, with reason selection.

- Moderator and admin visibility of any conversation, every view audit-logged.

- Moderation queue: dismiss, remove content, warn, suspend; reports involving minors flagged high priority.

### Ratings

- Star rating and optional comment after resolution, once per request.

- Tutor average rating on profile and in admin; low ratings flagged for review.

### Deliverables

- Real-time messaging with safeguarding controls

- Moderation queue and actions

- Ratings and feedback

### Needed from DX during this sprint

- Prohibited-word list and moderation escalation policy

- Named moderators for UAT

Acceptance: DX completes a scripted safeguarding test: masked contact details, report raised, moderator suspends a user, actions appear in the audit log.

## Sprint 9 — Learning Resources, Offline Access & Announcements

| Item | Detail |
| --- | --- |
| Weeks | Weeks 17–18 |
| Effort | 157 hours |
| Payment on acceptance | ZAR 65,000 |
| Sprint demo | Upload, approval, personalised library, offline download and a targeted announcement |

Objective: Give students one curriculum-aware place for study material, usable on limited data and offline.

### Resource library

- Upload of notes, course materials, past papers and video links with curriculum tagging.

- Approval workflow for tutor uploads; immediate publication for admin uploads.

- Personalised library, keyword search, filters, in-browser preview, bookmarks.

- View and download tracking for reporting.

### Copyright controls

- Upload declaration that the uploader has the right to share the material.

- Uploader attribution on every resource.

- Copyright report reason routed to moderation, with a documented takedown process.

### Offline & announcements

- Download resources for offline use with a managed storage limit and a Downloads area.

- Announcements with rich text, attachments, priority, targeting by pathway, institution type, grade, year and faculty.

- Scheduling, expiry, unread indicators and push or email delivery for important announcements.

### Deliverables

- Resource library with approval and personalisation

- Offline downloads

- Targeted and scheduled announcements

### Needed from DX during this sprint

- First batch of learning content for the launch subjects

Acceptance: DX publishes a resource and an announcement, and confirms targeting and offline download behave correctly.

## Sprint 10 — Community & Moderation

| Item | Detail |
| --- | --- |
| Weeks | Weeks 19–20 |
| Effort | 157 hours |
| Payment on acceptance | ZAR 65,000 |
| Sprint demo | Subject boards with questions, answers, voting and moderation |

Objective: Enable peer learning in a space that is moderated to the same standard as private conversations.

### Community

- Subject boards scoped to pathway and level, with questions, replies and images.

- Upvotes and accepted answers, markable by the author or a tutor.

- Search within boards; unanswered-question view so tutors can help where it matters.

- Escalation path from an unmatched help request into the community.

### Moderation

- Contact masking and prohibited-word flagging applied to all posts.

- Report, hide, edit, delete and lock threads; user warnings and suspensions.

- Consolidated moderation queue covering messages, posts, resources and users.

- All moderation actions audit-logged and reportable.

### Deliverables

- Community boards with moderation

- Unified moderation queue

Acceptance: DX posts, reports and moderates content end to end.

## Sprint 11 — Progress, Tutor Recognition, Analytics & Low-Data Mode

| Item | Detail |
| --- | --- |
| Weeks | Weeks 21–22 |
| Effort | 157 hours |
| Payment on acceptance | ZAR 65,000 |
| Sprint demo | Student progress, tutor recognition, the analytics dashboard and low-data mode |

Objective: Give users a reason to come back, give tutors a reason to stay, and give DX the data to see what is working.

### Progress & recognition

- Student progress: requests raised and resolved, subjects engaged, resources used, community contributions, activity streaks.

- Tutor performance: requests handled, acceptance and resolution times, average rating, resources published.

- Verified tutor badge, monthly tutor leaderboard, downloadable contribution certificate.

- Monthly impact summary emails to tutors and progress summaries to students.

### Analytics

- Product analytics instrumentation: onboarding funnel, request creation, time to first help, resource engagement, retention.

- Analytics dashboard for DX covering the KPIs agreed in the BRD.

### Low-data mode

- Profile toggle, on by default, suppressing image loading with tap-to-load placeholders and reduced preloading.

- Payload budgets enforced in the build, with image compression and modern formats.

### Deliverables

- Progress and performance views

- Tutor recognition features

- Analytics dashboard

- Low-data mode

Acceptance: DX reviews the analytics dashboard against real staging usage and confirms the recognition features.

## Sprint 12 — Admin Console, Reports, Monetisation Engine & In-App Support

| Item | Detail |
| --- | --- |
| Weeks | Weeks 23–24 |
| Effort | 157 hours |
| Payment on acceptance | ZAR 65,000 |
| Sprint demo | Full admin console, exports, monetisation settings and in-app help |

Objective: Hand DX complete operational control of the platform, including when and how it starts earning.

### Administration

- User management with search and filters by role, status, pathway, consent state and registration date.

- Administrator and moderator management with role assignment.

- Operational dashboard: registrations, active users, requests by status and subject, response and resolution times, tutor utilisation, pending verifications, pending resources, open reports.

- Exports to CSV and Excel; audit log viewer; system settings for every configurable rule.

### Monetisation engine

- Platform mode: free for everyone, or freemium.

- Free allowance configuration: requests per month, and whether resources and community remain free.

- Per-user overrides, including free for life, for bursary students, pilot schools and early adopters.

- Grandfathering by registration date so existing users keep free access.

- Quota display, warnings and a blocked state with an upgrade prompt rather than an error.

- Optional free trial period for new accounts.

### In-app support

- Admin-managed FAQ and help centre.

- Feedback and problem reporting with device and context attached, routed to an admin queue.

### Deliverables

- Complete admin console with reports and exports

- Monetisation engine, fully admin-controlled

- In-app help and feedback

### Needed from DX during this sprint

- Decision on launch monetisation mode and free allowance

Acceptance: DX operates the platform entirely from the admin console, including switching monetisation modes and granting free-for-life access.

## Sprint 13 — Payments & Subscriptions, PWA & Store Apps

| Item | Detail |
| --- | --- |
| Weeks | Weeks 25–26 |
| Effort | 157 hours |
| Payment on acceptance | ZAR 65,000 |
| Sprint demo | A live test subscription payment, and the app installed on an Android and an iOS device |

Objective: Connect payments to the monetisation engine and package the platform as installable apps.

### Payments

- South African payment gateway integration (PayFast or Yoco, confirmed in Sprint 1): card and instant EFT.

- Subscription plans, recurring billing, upgrades, downgrades and cancellation.

- Webhook handling, failed payment retries, dunning emails and grace periods.

- Tax invoices, payment history, refunds and reconciliation reporting for DX.

- Payments remain switched off until DX activates freemium mode.

### Mobile packaging

- Progressive Web App: installable, app icon, splash screen, offline shell, push notifications.

- Capacitor Android and iOS projects built from the same React code base.

- Native capabilities: push notifications, camera capture, file access, offline storage.

- Codemagic pipeline: tagged release builds, managed signing, automatic upload to TestFlight and Google Play internal testing.

- Store listings, screenshots, age ratings, privacy labels and Data Safety declarations.

### Deliverables

- Working payments against the monetisation engine, in test mode

- PWA plus Android and iOS builds distributed to DX testers

- Automated mobile build pipeline

### Needed from DX during this sprint

- Merchant account with the chosen gateway

- Apple Developer and Google Play accounts active

- Final terms, privacy policy and refund policy published

Acceptance: DX completes a test subscription purchase and installs the app from TestFlight and Play internal testing.

## Sprint 14 — Hardening, UAT, Store Submission & Go-Live

| Item | Detail |
| --- | --- |
| Weeks | Weeks 27–28 |
| Effort | 157 hours |
| Payment on acceptance | ZAR 65,000 |
| Sprint demo | Production launch |

Objective: Prove the platform is secure, fast and correct, then launch it on the web and in both app stores.

### Testing

- Full regression testing across browsers, devices and both store apps.

- Security testing against the OWASP Top 10, dependency scanning and remediation.

- Performance and load testing against the agreed launch capacity, with tuning.

- Accessibility check against WCAG 2.1 AA.

- Backup restore test and disaster recovery rehearsal on the production stack.

### Acceptance & launch

- UAT with DX testers across all roles, with defect triage and fixing.

- Production cutover: domain, SSL, environment configuration, queue workers, scheduler, monitoring and alerts.

- Curriculum and content loading, launch subjects switched on, first tutors verified.

- App store submission and review support for both stores.

- Training for administrators, moderators and lead tutors.

- Documentation handover: admin guide, user guide, deployment guide, API documentation, credentials.

### Deliverables

- Live production platform

- Apps published to Google Play and the Apple App Store

- Test reports, documentation and complete handover

### Needed from DX during this sprint

- UAT sign-off

- Launch communications and tutor cohort ready

Acceptance: DX signs off UAT; the platform is live in production with no open critical or high-severity defects.

# 5. Hypercare, Warranty and Handover

For 60 days after go-live, at no additional cost:

- Defects against the agreed scope are fixed at no charge.

- Stability, performance and error logs are monitored and tuned.

- Source code, documentation and all credentials are formally handed over.

- A transition to an ongoing support and maintenance plan is offered, quoted separately.

# 6. Risks and How They Are Managed

| Risk | Impact | Management |
| --- | --- | --- |
| Too few tutors for a subject at launch | High | Tutor registration opens in Sprint 6, twelve weeks before launch. Subjects go live only once minimum coverage is met, monitored on the coverage dashboard. |
| Harm to a minor through tutor contact | High | Guardian consent, tutor verification, on-platform messaging only, contact masking, moderator visibility, report and block, priority handling of minor-related reports. |
| Apple or Google account registration delays | Medium | Registration starts in Sprint 1 because organisation verification can take weeks. Store submission is not on the critical path until Sprint 14. |
| POPIA non-compliance | High | Privacy by design, consent records, data subject rights, retention rules, audit logs. DX appoints an Information Officer in Sprint 1. |
| Legal documents not ready for store submission | Medium | DX engages an attorney by Sprint 8. We supply the data-processing description at no charge. |
| Empty resource library at launch | Medium | Content loading is a named DX dependency with a Sprint 9 start and a Sprint 14 deadline. |
| Scope growth during delivery | Medium | Change control with written approval; non-urgent items scheduled for a later phase. |

# 7. What DX Must Provide

## 7.1 Accounts and services

| Item | Needed by | Notes |
| --- | --- | --- |
| Apple Developer Program | Sprint 1 (start) | Organisation account needs a D-U-N-S number; allow 1–3 weeks |
| Google Play Console | Sprint 1 (start) | Organisation account avoids new-developer testing restrictions |
| VPS root / WHM access and domain DNS | Sprint 3 | For environment setup |
| Transactional email service | Sprint 3 | Platform email must not be sent through cPanel mail |
| Off-server backup storage | Sprint 3 | Backups on the same server are not backups |
| Cloudflare account | Sprint 3 | DNS, CDN, WAF |
| Firebase project | Sprint 13 | Push notifications |
| Payment gateway merchant account | Sprint 13 | PayFast or Yoco |
| Attorney-drafted terms, privacy policy, consent wording, tutor agreement | Sprint 8 | Required for store submission |
| Information Officer registered with the Information Regulator | Sprint 1 | POPIA requirement |

## 7.2 Content, people and decisions

- Curriculum master data for all pathways (Sprint 1).

- Policy decisions: minimum age, consent method, verification documents, monetisation model (Sprint 1).

- Students and tutors for the usability walkthrough (Sprint 3) and UAT (Sprint 14).

- Tutor recruitment from Sprint 6, targeting the minimum coverage for launch subjects.

- At least ten approved resources per launch subject (Sprints 9–14).

- Brand assets, app store screenshots input and launch communications.

# 8. Commercial Summary

| Item | Sprints | Hours | ZAR |
| --- | --- | --- | --- |
| Delivery of the platform as described above | 14 | 2,198 | 910,000 |
| Hypercare and warranty (60 days) | — | Included | — |
| Total | 14 | 2,198 | 910,000 |

- No upfront payment. ZAR 65,000 is invoiced on acceptance of each sprint, payable within 7 days.

- Exclusive of applicable taxes. Third-party running costs (hosting, email, storage, developer accounts, gateway fees) are paid by DX.

- Support and maintenance after the warranty period is quoted separately as a monthly retainer.

- Prices are based on ZAR 16.60 per USD; if the rate at invoicing differs by more than 5%, remaining invoices are adjusted proportionately.

# 9. Approval

Approval confirms this sprint plan as the delivery baseline for DX Student Help.

| For The X Student Help (PTY) LTD | For Mayura Consultancy Services |
| --- | --- |
| Name: Thabo Mkhize | Name: Srini |
| Title: | Title: Director |
| Signature: | Signature: |
| Date: | Date: |